NPFC-2023-SSC PS12-WP01 (Rev. 1)

Five-Year Work Plan of the SSC PS

Abstract: The Five-Year Work Plan of the SSC PS has been updated by the SSC PS Chair. Members are invited to review the work plan during the SSC PS12 meeting.

Priority list:

- Conduct a stock assessment update based on BSSPM analyses

- Further investigate improvements to the BSSPM

- Develop an age/size-structured model

- Develop a list of plausible ranges for biological parameters

- Develop databases to support age/size-structured models

- Continue joint CPUE work to incorporate broader spatial and temporal coverage

- Update the biomass estimate using the existing method (swept area method)

- Develop spatio-temporal model for the biomass estimate

- Further refine the catchability coefficient of the Japanese survey and characterize its variance

- Continue exploring climate indices to explain impacts on Pacific saury stock productivity

- Support any technical work on MSE under SWG MSE PS

- Further evaluate the reason and the basis for the perception that total bycatch in all NPFC fisheries is low

[H] and [M] indicate high and medium priorities. Cells with “TBD” depend on the progress of data preparation and analytical works.

| ITEM | 2023 | 2024 | 2025 | 2026 | 2027 |
| --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |
| Update & improvement of biomass survey index | Continue regular review [H] of 1) survey plan 2) analytical work 3) any related issues including experiments to produce absolute biomass index and additional surveys by other Members to increase coverage | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] |
| Update & improvement of CPUE indices | Continue review of outcomes of regular update and analytical works [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] |
| Development of joint CPUE index | Continue review of outcomes of regular update and analytical works [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] |
| Regular update of the existing SA |  |  |  |  |  |
| Routine update BSSPM as a benchmark | Continue review of outcomes of regular BSSPM update [H] 1) | Same as on the left [H] 1) | Same as on the left [H] 1) | Same as on the left [H]1) | Same as on the left [H]1) |
| Improvement and further investigation of BSSPM | Review any outcomes of improvements, inter alia in light of possible incorporation of environmental information [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] | Same as on the left [H] |
| Toward age/size-structured models (ASSMs) |  |  |  |  |  |
| Data inventory (CPUE and size/age in space and time) |  | Explore age-specific abundance indices or recruitment indices. Conditional age at length information. Spatio-temporal variation of size composition. | TBD2) | TBD2) | TBD2) |
| Summarizing available information on PS biology |  | Update regularly, specifically maturity ogive and growth function | Continue | Continue | Continue |
| Development of models |  | Review preliminary models to be evaluated | Finalize development of a new stock assessment model | Test the age-structured model capabilities for Bayesian estimation, simulation testing and MSE work | External review |
| Uncertainty in models (possible link with OM grid under MSE) |  | Refine the plausible range of values of key biological parameters. Refine assumptions about prior distributions and the ranges for model parameters. | Continue | Continue | Continue |

1) As a backup method as well as an underlying assessment method used in a management procedure, it seems sensible to keep this as one of reference assessment models.

2) These items might be re-structured depending on the progress of preparation of data and biological information as well as the development of models.