NPFC-2025-TWG CMSA10-WP01

TWG CMSA Work Plan, 2025-2029

Members will review and updated the TWG CMSA work plan up to 2029. The Work Plan will be submitted to the SC10 meeting for review.

FIVE-YEAR WORK PLAN

Technical Working Group on Chub Mackerel Stock Assessment (TWG CMSA)

[2024 summer to be removed and a new column for 2029 to be added]

Priority list:

- Data preparation and review of biological information

- Conduct stock assessment of chub mackerel

- Set biological reference points

- Provide scientific advice on the management of chub mackerel stock to the Commission

- Explore the influence of climate changes on chub mackerel stock

- Regularly update and refine inputs

| ITEM | 2024 summer | 2025 winter | 2025 summer | 2026 | 2027 | 2028 | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |  |  |
| Research survey indices | Finalize data used for the stock assessment | Update |  | Update | Update | Update | Research survey indices have been finalized and used for stock assessment. |
| CPUE indices | Finalized CPUE standardization | Update |  | Update | Update | Update | CPUE standardization has been finalized and used for stock assessment. |
| Catch data/catch composition | Finalize data used for the stock assessment | Update CAA data |  | Update | Update | Update | Catch data and catch composition have been finalized and used for stock assessment. |
| Biological parameters (maturity, M, weight) | Finalize assumptions for the stock assessment | - Review biological parameters - Discuss setting of natural mortality at age for future base cases - Explore mechanisms of temporal change of maturity at age and weight at age used for calculation of reference points and future projections - Bridge the gaps in maturity at age data among Members |  | Review biological parameters | Review biological parameters | Review biological parameters | Assumptions on biological parameters have been finalized and used for stock assessment. |
| Quarterly fishery data (CAA, WAA, Maturity-at-age) | - Submit quarterly fishery data - Share and standardize age-counting rule | - Update quarterly fishery data - Share and standardize age-counting rule |  | Update | Update | Update | Quarterly fishery data has been submitted. |
| Stock assessment |  |  |  |  |  |  |  |
| Benchmark stock assessment | Complete stock assessment with the selected SA model |  | Update SA | Update SA | Update SA | Update SA | Benchmark stock assessment has been conducted. |
| Improvement and further investigation of the selected model |  | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model |  |
| New stock assessment models |  |  | Explore new stock assessment models, if available | Explore new stock assessment models, if available | Explore new stock assessment models, if available | Explore new stock assessment models, if available |  |
| Reference points, HCR, future projections and MSE |  |  |  |  |  |  |  |
| Set biological reference points (limit and target) | Review and calculate reference points | Discuss how to calculate biological reference points in consideration of nature of temporal changes in biological parameters | Review and calculate reference points | Review and calculate reference points | Review and calculate reference points | Review and calculate reference points | Commonly used reference points are reviewed, and calculation with the results of SA have been completed |
| Develop future projections | Provide preliminary results of future projection, if possible | - Initiate discussion of harvest control rule (HCR) to determined future catch, according to traits of CM biological parameters - Explore more sophisticated method for conducting future projections with more uncertainties | Candidates of HCR are tested in future projections | Selection of HCR | Improvement | Improvement | Preliminary results of future projection have been provided. |
| Develop Management Strategy Evaluation (MSE) |  | Start discussion | Development | Trial to be used for selection of HCR | Improvement | Improvement |  |