## Sheet2
NPFC-2025-COM09-WP08 Rev.3
TCC WORK PLAN 2025-2026 (including SWG OPs and PD)
No. | ISSUE | LEAD | ACTION / TIMELINE
1 | Transshipment
| Transshipment amendment implementation | SWG OPs/Secretariat | Continue to track issues related to implementation of transshipment measure.
2 | Observer program / EM
| Implement ROP for transshipment | TCC/SWG | Identify and track tasks necessary for April 2026 implementation
| Continue planning for broader NPFC observer program | TCC/SC (Chairs) | Continue dialogue between TCC and SC Chairs on what data should be collected
3 | Vessel Registry
| Update Vessel registry to address errors in current and historic data | Secretariat/Members | Secretariat to work with Members to confirm data in Registry
| Information gaps in Vessel Registry | Secretariat/SWG Ops | Secretariat to continue "cleanup" of VR, removing and identifying "information gaps" in Registry.
SWG Ops to review and identify gaps and recommend cooperation from Members to update the Registry with current details
| Para 4, Annex 2 of CMM2023-01 | SWG Ops | Amend "or" to "in paragraph 4 of Annex 2 of Vessel Registry CMM 2023-01
4 | CMS
| Multi year work plan in para. 27 of CMS CMM | SWG PD | Auto- responses, corrective actions, develop audit points, and consider Executive Summary feedback on improvements to the CMS
5 | HSBI
| Update Implementation plan | SWG Ops | Continue to develop HSBI plan for review at TCC08
| Enhancements to the HSBI Events page are required to facilitate data analysis | Secretariat | Establish mechanism for reporting aerial surveillance results on Events page
Work with service provider to seek options/costs of enhancing the data entry process for HSBI reports to enable direct entry of reports by Members and automated report generation by Secretariat.
6 | Port Inspection program
| Port state measure draft CMM | SWG PD /OPS Secretariat | Continue work on PSM draft measure, including exploring notification options in view to considering this measure in 2026 for possible adoption.
7 | Performance Review
| Consideration of TCC relevant recommendations consistent with direction from Commission | Secretariat/COM/SC/TCC/ FAC Chairs | 1. The Commission agreed to work intersessionally to continue to update the matrix by:
(a) tasking the Secretariat, in consultation with the Chairs of the Commission and its subsidiary bodies, to update the matrix based on the outcomes of the meetings of the Commission and its subsidiary bodies,
(b) circulating the updated matrix among Members to seek comments on the priority and suggested way forward for each recommendation,
(c) compiling comments from Members and circulating the revised matrix,
(d) repeating this process to the extent possible during the intersessional period.
8 | Effort Controls
| Continue historic existing levels discussion | Secretariat/SWG/SC | For review at TCC08 Continue work on this issue, considering options developed at TCC; (b) complie in one document when each CMM mentioning historical level was first adopted; (c) Seek clarity on data sources from Members fro the complied table; (d) Work to reconcile Member data with Secreatriat records; (e) Consider amending CMMs that reference historical fishing levcel to provide greater clarity; (f) Further consiter criteria purpose for defining historical fishing level, including: (i) a period from CMM adoption year minus one through adoption year minus three; (ii) A three-year period from the CMM adoption year going back three years; (iii) A timeframe relecting the development of the fishery; or (iv) Other appropriate timeframes from on to multiple years
9 | Annual Report Template
| Update template | Secretariat/SWGs SC | Review existing reporting template and update to align authorizations/active vessels to their respective fisheries and propose other appropriate revisions at TCC089
10 | Data Standard
| Data standardization draft CMM | SWG PD | Await progress from SC -SWG Data