NPFC-2025-TWG CMSA011-WP01

TWG CMSA Work Plan, 2025-2029

Members reviewed and updated the TWG CMSA work plan up to 2029. The Work Plan will be submitted to the SC10 meeting for review.

FIVE-YEAR WORK PLAN

Technical Working Group on Chub Mackerel Stock Assessment (TWG CMSA)

Priority list:

- Data preparation and review of biological information

- Conduct stock assessment of chub mackerel

- Set biological reference points

- Provide scientific advice on the management of chub mackerel stock to the Commission

- Explore the influence of climate changes on chub mackerel stock

- Regularly update and refine inputs

| ITEM | 2025 | 2026 | 2027 | 2028 | 2029 | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |  |
| Research survey indices | Update | Update | Update | Update |  | Research survey indices have been finalized and used for stock assessment. |
| CPUE indices | Update | Update | Update | Update |  | CPUE standardization has been finalized and used for stock assessment. |
| Catch data/catch composition | Update | Update | Update | Update |  | Catch data and catch composition have been finalized and used for stock assessment. |
| Biological parameters (maturity, M, weight) | Review biological parameters | Review biological parameters | Review biological parameters | Review biological parameters |  | Assumptions on biological parameters have been finalized and used for stock assessment. |
| Quarterly fishery data (CAA, WAA, Maturity-at-age) | Update | Update | Update | Update |  | Quarterly fishery data has been submitted. |
| Stock assessment |  |  |  |  |  |  |
| Benchmark stock assessment | Update SA | Update SA | Update SA | Update SA |  | Benchmark stock assessment has been conducted. |
| Improvement and further investigation of the selected model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model |  | Done and ongoing. |
| New stock assessment models | Explore new stock assessment models, if available | Explore new stock assessment models, if available | Explore new stock assessment models, if available | Explore new stock assessment models, if available |  |  |
| Reference points, HCR, future projections and MSE |  |  |  |  |  |  |
| Set biological reference points (limit and target) | Review and calculate reference points | Review and calculate reference points | Review and calculate reference points | Review and calculate reference points |  | Commonly used reference points are reviewed, and calculation with the results of SA has been completed |
| Develop future projections |  | Candidates of HCR are tested in future projections | Selection of HCR | Improvement |  | Results of future projection have been provided. |