## Sheet1
Progress on the Five-year Work Plan to implement NPAFC/NPFC Memorandum of Cooperation (MOC) (endorsed by NPFC and NPAFC in 2023)
April, 2026
NPAFC Secretariat
Exchange of data and information in accordance with the information-sharing and data confidentiality policies of each Commission;
• Create a SharePoint inter-commission communication system to share news, reports, guideline documents, and other information relevant to the management of the mutual area of interest in an easily accessible form.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2023– June 2024 | NPAFC/NPFC SharePoint Terms of Reference to describe structure, capabilities, access rights, and control issues | Terms of Reference (ToR) agreed by both commissions – September 15, 2023 | Terms of Reference of the NPAFC/NPFC data sharing platform (Appendix 1) was approved by the NPFC at its COM09 in March 2025, and by NPAFC at its 32nd Annual Meeting in May 2025. In July 2025, both Secretariat met and discussed operation of the data sharing platform, and recognized that the contents to be shared through the platform need to be more clearly identified.
| NPAFC/NPFC SharePoint service in a test mode | Test mode – December 31, 2023
| NPAFC/NPFC SharePoint service in full operational mode | Full operational mode – June 30, 2024
• Establish a mechanism of general information exchange (e.g., MCS activity information, fleet activity information, map of catch and fishing efforts).
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2022– December 2023 | NPAFC/NPFC communication and information exchange plan | A plan agreed by the commissions – First half of 2023 | The NPAFC/NPFC Secretariats exchange relevant information by e-mail as necessary.
| Regular mutual email conferences to exchange MCS and enforcement activities information | Summer–autumn of 2023 | Potential contents for the regular mutual email conferences have not been identified.
2022–2025 | NPFC historical footprint (catch and fishing efforts) of the fisheries | Pacific saury, Japanese sardine, chub and blue mackerels, Japanese flying squid, neon flying squid, North Pacific armorhead, splendid alfonsino – available on the NPFC website | Completed/Ongoing (as written on the left column)
| Annual data reporting/sharing of Pacific salmon as by-catch by NPFC fishing vessels (voluntary) |  | So far, no Pacific salmon bycatch data has been shered. Pacific salmon bycatch data to be reported in NPFC may be shared voluntarily in the NPAFC/NPFC data sharing platform or through other general information exchange considering data security policies of the Commissions.
| Interactive Mapping System (IMS) for the INPFC/NPAFC High-Seas Salmonid Tag- Recovery Database | IMS in a test mode with limited access – May 2023. IMS in full operational mode – May 2024 | Completed/Ongoing (The IMS is in full operation since June 2024.)
• Establish a practice of sharing information on suspicious fishing vessels identified in overlapping convention area including stateless vessels and unregistered vessels.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2023– June 2024 | Vessel of Interest folder which has been treated as confidential at the NPAFC/NPFC Sharepoint | Vessel of Interest folder description is included in the ToR agreed by the commissions – September 15, 2023 | The NPAFC List of Vessel of Interest are included as a content of the NPAFC/NPFC SharePoint in its Terms of Reference. However, the contents of the SharePoint folder needs to be more clearly identified.
Vessel of Interest information is included in the folder – June 30, 2024
Collaboration on research efforts relating to stocks and species of mutual interest, including stock assessments;
• Implement Pan-Pacific research survey plans in winter 2022, organize a comprehensive study of its outcome at the special session of the IYS Synthesis Symposium.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2021– February 2022 | NPFC suggestions to the NPAFC Pan-Pacific High Seas Research Expedition cruise plans. | NPFC proposal submitted to the NPAFC – November 2021 | Completed (as written on the left column)
| NPFC participation in the country leads meetings to coordinate/contribute to the Expedition plans. | NPFC Science Manager / Scientific Committee Chairperson participates in the country leads meetings in August 2021–February 2022 | Completed (as written on the left column)
|  | NPAFC presented a report on the expedition finding after its completion in 2022 | Completed (as written on the left, and NPAFC published the report as NPAFC Technical Report Nos. 20 and 22 in 2023.)
• Coordinate research activities identified in the NPFC/PICES and NPAFC/PICES Frameworks for Enhanced Scientific Cooperation in the North Pacific Ocean.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
October 2023– May 2025 | Coordination of research activities identified in the NPFC/PICES and NPAFC/PICES Frameworks |  | A multi-year initiative Basin-Scale Events to Coastal Impacts (BECI) has been identified as one of the potential coordinations of research activities among NPFC/NPAFC/PICES. Details will be discussed by the commissions.
Implementation of conservation and management measures for stocks and species of mutual interest;
• Establish a mechanism to share the IUU vessel list of each Commission and its related information.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2021– May 2023 | Accessible links to the NPAFC and NPFC IUU vessel list on both Commissions’ website | NPAFC is developing the IUU vessel listing process with a study group, and the NPAFC IUU vessel list is expected to be established for the first time – May 2023 | NPFC IUU vessel list has been linked on NPAFC website. NPAFC approved NPAFC IUU Vessel List for 2025, which is empty, in May 2025. Draft NPAFC IUU Vessel List for 2026 will be discussed at the 32nd NPAFC Annual Meeting in May 2026. Once the NPAFC IUU Vessel List will be adopted, the List will be linked on the NPFC website.
• Expand cooperation to collect and share information relating to species of special interest for each Commission.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
August 2021– December 2025 | Information exchange on research cruise plans that can collect information on Pacific salmon and NPFC priority species | Lists of scientific cruise plans are exchanged – May 2022 NPAFC/NPFC/PICES Topic Session (or Workshop) on this issue is proposed for October 2023 at the PICES Annual Meeting | NPAFC/NPFC/PICES Topic Session (or Workshop) on the issue has not been held at the PICES Annual Meeting. NPAFC member countries' research cruise plan in 2026 will be delivered to NPFC Secretariat after the NPAFC Annual Meeting in May 2026.
| Mutual scientific documents and publications on Pacific salmon and NPFC priority species distribution, relationships, and potential impact | Mutual scientific documents and publications on Pacific salmon and NPFC priority species are published in 2023–2025 | A report of the potential joint workshop, which NPAFC Secretariat has been consulting with NPFC Secretariat, would be the scientific publication of mutual interests. NPAFC Workshop on Interactions Between Fisheries and Anadromous Fish in the Pacific High Seas and NPAFC Workshop on Interactions Between Salmon, Ecosystems, and Climate: From Mechanisms to Predictive Models will be held in May 2026. These workshops may lead to a concept of scientific publication of mutual interests.
• Develop, publish, and distribute public information about conservation on the high seas and consequences of IUU activity.
Timeline | Deliverables | Milestones (as of May 2023) | Progress (as of April 2026)
2021–2025 | News releases and journal articles on the Commissions activities related to high seas resources conservation, MCS, and law enforcement | Secretariats annually exchange information on the relevant publications | Ongoing (as written on the left column)