## Sheet2
Adopted on the screen
NPFC-2026-TCC09-WP10 Rev.4
TCC WORK PLAN 2026-2027 (including SWG OPs and PD)
No. | ISSUE | LEAD | ACTION / TIMELINE
1 | Transshipment
| Transshipment and TOP implementation | SWG OPs/Secretariat | Continue to track issues related to implementation of transshipment and TOP measure.
|  | SWG PD/ Ops | Review CMMs to consider application of Transshipment and Transshipment Observer Program inside EEZ
2 | Observer program / EM
| Broader NPFC observer program | TCC/ SWG PD | Task SWG PD with development of a white paper/information paper on what TCC might want from a ROP, including consideration of other data collection methods-such as EM , Members Observer programs, port sampling. Bring reccommendation to TCC10
3 | Vessel Registry
| Update Vessel registry to address errors in current and historic data | Secretariat/Members | Secretariat to work with Members to confirm data in Registry
| Address Information gaps, Vessel and gear coding and systemic issues in Vessel Registry | Secretariat/SWG Ops | Secretariat to continue "cleanup" of VR, removing and identifying "information gaps" in Registry.
SWG Ops to review and identify gaps,coding and systemic issues and recommend cooperation from Members to update the Registry with current details
4 | CMS
| Multi year work plan in para. 27 of CMS CMM | SWG PD | Auto- responses, corrective actions, develop audit points, and consider Executive Summary feedback on improvements to the CMS
5 | HSBI/MCS
| Technical support to HSBI | SWG Ops | SWG Ops to work with Sec to develop and deliver a workshop or series of workshops to support MCS program managers and inspectors with implementation of the HSBI cmm and associated reporting requirements and online tools. Over the past few years, NPFC Members have increased their participation in compliance monitoring and inspection work and SWG Ops would be an appropriate forum to promote cooperation and exchange of best practices amongst technical experts and MCS representatives of inspection authorities.
| Enhancements to the HSBI Events page are required to facilitate data analysis | Secretariat
Work with service provider to seek options/costs of enhancing the data entry process for HSBI reports to enable direct entry of reports by Members and automated report generation by Secretariat.
7 | Performance Review
| Consideration of TCC relevant recommendations consistent with direction from Commission | Secretariat/COM/SC/TCC/ FAC Chairs | 1. The Commission agreed to work intersessionally to continue to update the matrix by:
(a) tasking the Secretariat, in consultation with the Chairs of the Commission and its subsidiary bodies, to update the matrix based on the outcomes of the meetings of the Commission and its subsidiary bodies,
(b) circulating the updated matrix among Members to seek comments on the priority and suggested way forward for each recommendation,
(c) compiling comments from Members and circulating the revised matrix,
(d) repeating this process to the extent possible during the intersessional period.
8 | Effort Controls
| Continue historic existing levels discussion | Secretariat/SWG OPs | All Members will submit data to the Secretariat 1 week prior to first SWG Ops meeting. If Members have already submitted data, they do not need to re-submit, but may update/supplement. Data will be for those years in the table presented at COM10; Members may submit additional data, if they want. SWG OPs will use that data to continue discussing a definition of historic existing level, taking into account those options presented at COM10 by the SWG OPs, definitions submitted by Members at COM10, and dicussions held at COM10.
..
9 | VMS
| NAF Format | SWG OPs | Review options for incorporation of NAF format in VMS CMM, including consideration of Member issues regarding inclusion of mandatory reporting of IMO number
10 | IUU Vessel List
| Consideration of Cross-Listing | SWG PD | Consider amendment to IUU CMM for cross-listing of other RFMO IUU Vessel Lists, including the process/procedures for doing so.
| Review CMM 2024-02 | SWG PD | Review the entire measure, taking into account the practices of other RFMOs.