NPFC-2026-SSC JS01-IP05 (Rev. 1)

Table of intersessional activities and timelines for the SSC JS in the 2026 operational year

| Activity/Task | Deadline | Responsibility and Reference/Comment |
| --- | --- | --- |
| Members |  |  |
| Updates of biological information for JS | 9 Jan 2027 (two months before SSC JS02) | - If available - WP or IP |
| Standardized fishery-dependent and fishery-independent abundance indices up to 2025 (2026, if possible) | Same as above | - Members operating JS fisheries - WP - See CPUE Standardization Protocol for CM |
| Stock assessment modelling results | 23 Feb 2027 (two weeks before SSC JS02) | - If available - WP |
| Research on climate change impacts on JS | Same as above | - If available - WP or IP |
| Members' sampling programs for transshipped catch | Same as above | - Members conducting transshipment of JS - WP or IP |
| Fisheries-independent indicators (from SC10): i. Egg abundance in East Japan ii. Acoustic survey in autumn (Sep-Oct) (abundance of age 0 fish) iii. Trawling survey in summer (Jun-Jul) (abundance of age 0 fish) iv. Trawling survey in summer (Jun-Jul) (abundance of age 1 fish) v. Standardized CPUE from China’s summer survey | Same as above | - Members conducting research surveys - WP |
| Fisheries-dependent indicators: None identified in SC10. | Same as above | - Members operating JS fisheries - WP |
| Updates on Members' fishery status and research activities up to 2026 | Same as above | - Members operating JS fisheries and/or conducting research surveys - IP (ppt slides) |
| Chair/Secretariat/Invited expert |  |  |
| Data call | During SSC JS01 (26-28 Jul 2026) | Secretariat/Chair |
| Invited expert’s roles and tasks for the 2026 operational year (annexed to SSC NFS03 report) | Same as above | Secretariat/Chair |
| Species summary for JS update | 23 Dec 2026 | Chair/Secretariat |
| Annotated Indicative Schedule | 23 Feb 2027 (two weeks before SSC JS02) | Secretariat |
| Work Plan of the SSC JS | Same as above | Chair/Secretariat Update up to 2031; including climate change issues |