NPFC-2026-SSC JS01-WP07 (Rev. 1)

SSC JS Work Plan, 2026-2030

Members reviewed and endorsed the SSC JS work plan for 2026-2030. The Work Plan will be submitted to the SC for review.

FIVE-YEAR WORK PLAN

Small Scientific Committee on Japanese Sardine (SSC JS)

Priority list:

- Data preparation and review of biological information

- Conduct stock assessment of Japanese sardine

- Set biological reference points

- Provide scientific advice on the management of Japanese sardine stock to the Commission

- Explore the influence of climate changes on Japanese sardine stock

- Regularly update and refine inputs

| ITEM | 2026 | 2027 | 2028 | 2029 | 2030 | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |  |
| Research survey indices | Submit standardized fishery-independent indices | Update | Update | Update | Update |  |
| CPUE indices | Submit standardized CPUE | Update | Update | Update | Update |  |
| Catch data/catch composition | Provide catch composition data | Update | Update | Update | Update |  |
| Biological parameters (maturity, M, weight) | Review biological parameters | Review biological parameters | Review biological parameters | Review biological parameters | Review biological parameters |  |
| Fishery data (CAA, WAA, Maturity-at-age) | Provide fishery data | Update | Update | Update | Update |  |
| Stock assessment |  |  |  |  |  |  |
| Benchmark stock assessment |  | Conduct provisional stock assessment | Update SA | Update SA | Update SA |  |
| Improvement and further investigation of the selected model |  |  | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model | Review and improve, if needed, the SA model |  |
| Reference points, HCR, future projections and MSE |  |  |  |  |  |  |
| Set biological reference points (limit and target) |  | Provide candidate reference points | Review and calculate reference points | Review and calculate reference points | Review and calculate reference points |  |
| Develop future projections |  | Provide future projections, if possible | Same as on the left |  |  |  |