NPFC-2026-SSC NFS04-WP01 (Rev. 1)

Five-Year Work Plan of the SSC NFS

Abstract: The Five-Year Work Plan of the SSC NFS was updated by the Chair. Members reviewed the work plan during the SSC NFS04 meeting and recommendeded it to the SC.

Priority list:

- Continue research to appropriately separate two cohorts using spatial and age/size characteristics

- Continue CPUE standardization work

- Continue research and literature reviews to better understand the biological characteristic (e.g., growth rate, natural mortality), life history (e.g., cohorts associated with spawning timing and location, feeding and spawning migration) of the species and population structure (e.g. genetic analysis)

- Conduct a stock assessment based on surplus production model

- Further investigate improvements to the surplus production model

- Explore and develop alternative approaches, such as the management strategy evaluation framework and data-limited management procedures, to provide effective management advice

- Conduct research and literature reviews to better understand the factors driving abundance fluctuations (including climate change) in this short-lived species

- Develop other models e.g., age/size-structured model

- Develop databases to support age/size-structured models

| ITEM | 2026 | 2027 | 2028 | 2029 | 2030 | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| Regular update of inputs |  |  |  |  |  |  |
| Update & improvement of CPUE indices | Submit standardized CPUE by each member | Update | Update | Update | Update | Updated CPUE indices of Japanese survey and Chinese, Japanese and Chinese Taipei’s squid fisheries. |
| Joint CPUE standardization | Conduct joint CPUE standardization | Update | Update | Update | Update | Invited expert updated joint CPUE standardization and R package was shared with Members. |
| Regular update of surplus production model |  |  |  |  |  |  |
| Update and review of surplus production model and other stock assessment models | Conduct preliminary stock assessment using standardized CPUE from each member | Conduct benchmark stock assessment | Update | Update | Update | China and Japan conducted preliminary stock assessment using JABBA and SPiCT, respectively. |
| Improvement and further investigation of surplus production model | Review any outcomes of improvements, inter alia in light of possible incorporation of environmental information | Same as on the left | Same as on the left | Same as on the left | Same as on the left | No progress |
| NFS biology |  |  |  |  |  |  |
| Data inventory (CPUE and size/age in space and time from research surveys) |  | Conditional age at length information. Spatio-temporal variation of size composition. | TBD | TBD | TBD | Information on size composition was shared by some Members |
| Summarizing available information on neon flying squid biology |  | Update regularly, specifically maturity ogive, growth function by cohort, W-L relationship and its variability. Conduct research and literature reviews to better understand the factors driving abundance fluctuations | Continue | Continue | Continue | Updated information on spawning ground and age composition |
| Toward other approaches to provide management advises |  |  |  |  |  |  |
| MSE or data-limited management procedures | Explore methods and tools for MSE | Explore methods and tools for MSE | TBD | TBD | TBD | Pew presented simulation methods for the assessment and MSE for short-lived species |
| Review other successful (or unsuccessful) stock assessment and management practices for squid or other short-lived species globally to inform SSC NFS work | No planned task | No planned task | TBD | TBD | TBD | Invited expert reviewed stock assessment methods and management measures for squid and other short-lived species |